## Project Page
Task ID | Description | Planned Hours | Actual Hours | Planned Delivery Date | Actual Delivery Date | Task Status | OTD | FTR | Effort Variance | Remarks | EMPID
T016 |  | 70 | 63 | 2021-01-05 |  | Rework |  | NO | -10% |  | ED3002
T017 |  | 90 | 99 | 2021-06-08 | 2021-06-07 | Delivered | OTD | YES | 10% |  | ED3002
T018 |  | 169 | 153 | 2021-02-07 |  | Rework |  | NO | -9.467% |  | ED3002
T019 |  | 54 | 54 | 2021-07-05 | 2021-07-05 | Delivered | OTD |  | 0% |  | ED3002
T020 |  | 81 | 81 | 2021-04-04 |  | Rework |  | NO | 0% |  | ED3002
T021 |  | 117 | 117 | 2021-07-20 | 2021-07-19 | Delivered | OTD | YES | 0% |  | ED3002
T022 |  | 72 | 81 | 2021-05-30 | 2021-08-02 | Delivered | Non OTD |  | 12.5% |  | ED3002
T023 |  | 18 | 18 | 2021-08-18 | 2021-08-11 | Delivered | OTD | YES | 0% |  | ED3002
T024 |  | 9 | 9 | 2021-07-25 | 2021-08-13 | Delivered | Non OTD |  | 0% |  | ED3002
T025 |  | 63 | 63 | 2021-08-22 | 2021-08-14 | Delivered | OTD | YES | 0% |  | ED3002
T026 |  | 9 | 9 | 2021-09-19 | 2021-08-22 | Delivered | OTD | YES | 0% |  | ED3002
T027 |  | 63 | 63 | 2021-10-17 | 2021-08-23 | Delivered | OTD | YES | 0% |  | ED3002
T028 |  | 45 | 54 | 2021-11-14 | 2021-08-30 | Delivered | OTD | YES | 20% |  | ED3002
T029 |  | 9 | 18 | 2021-12-12 | 2021-09-05 | Delivered | OTD | NO | 100% |  | ED3002
T030 |  | 36 | 36 | 2021-12-09 | 2021-09-07 | Delivered | OTD | YES | 0% |  | ED3002
Formulas:
Actual Delivery Date = IF(AND(Project_Tracker[[#This Row],[Task Status]]="Delivered", ISBLANK(Project_Tracker[[#This Row],[Planned Delivery Date]]) = FALSE), XLOOKUP(Project_Tracker[[#This Row],[Task ID]],Daily_Tracker[Task ID],Daily_Tracker[[Date ]], "",0,),"")

## Daily Tracker
Date | Task ID | Status | Hours | Remark | EMPID
2021-06-01 | T016 | In Work | 9 |  | ED3002
2021-06-02 | T016 | In Work | 9 |  | ED3002
2021-06-03 | T016 | In Work | 9 |  | ED3002
2021-06-04 | T016 | In Work | 9 |  | ED3002
2021-06-05 | T016 | In Work | 9 |  | ED3002
2021-06-06 | T016 | Delivered | 9 |  | ED3002
2021-06-07 | T017 | In Work | 9 |  | ED3002
2021-06-08 | T017 | In Work | 9 |  | ED3002
2021-06-09 | T017 | In Work | 9 |  | ED3002
2021-06-10 | T017 | In Work | 9 |  | ED3002
2021-06-11 | T017 | In Work | 9 |  | ED3002
2021-06-12 | T017 | In Work | 9 |  | ED3002
2021-06-13 | T017 | In Work | 9 |  | ED3002
2021-06-14 | T017 | In Work | 9 |  | ED3002
2021-06-15 | T017 | In Work | 9 |  | ED3002
2021-06-16 | T017 | In Work | 9 |  | ED3002
2021-06-17 | T017 | Delivered | 9 |  | ED3002
2021-06-18 | T018 | In Work | 9 |  | ED3002
2021-06-19 | T018 | In Work | 9 |  | ED3002
2021-06-20 | T018 | In Work | 9 |  | ED3002
2021-06-21 | T018 | In Work | 9 |  | ED3002
2021-06-22 | T018 | In Work | 9 |  | ED3002
2021-06-23 | T018 | In Work | 9 |  | ED3002
2021-06-24 | T018 | In Work | 9 |  | ED3002
2021-06-25 | T018 | In Work | 9 |  | ED3002
2021-06-26 | T018 | In Work | 9 |  | ED3002
2021-06-27 | T018 | In Work | 9 |  | ED3002
2021-06-28 | T018 | In Work | 9 |  | ED3002
2021-06-29 | T018 | In Work | 9 |  | ED3002
2021-06-30 | T018 | In Work | 9 |  | ED3002
2021-07-01 | T018 | In Work | 9 |  | ED3002
2021-07-02 | T018 | In Work | 9 |  | ED3002
2021-07-03 | T018 | Delivered | 9 |  | ED3002
2021-07-04 | T016 | Rework | 9 |  | ED3002
2021-07-05 | T019 | In Work | 9 |  | ED3002
2021-07-06 | T019 | In Work | 9 |  | ED3002
2021-07-07 | T019 | In Work | 9 |  | ED3002
2021-07-08 | T019 | In Work | 9 |  | ED3002
2021-07-09 | T019 | In Work | 9 |  | ED3002
2021-07-10 | T019 | Delivered | 9 |  | ED3002
2021-07-11 | T020 | In Work | 9 |  | ED3002
2021-07-12 | T020 | In Work | 9 |  | ED3002
2021-07-13 | T020 | In Work | 9 |  | ED3002
2021-07-14 | T020 | In Work | 9 |  | ED3002
2021-07-15 | T020 | In Work | 9 |  | ED3002
2021-07-16 | T020 | In Work | 9 |  | ED3002
2021-07-17 | T020 | In Work | 9 |  | ED3002
2021-07-18 | T020 | Delivered | 9 |  | ED3002
2021-07-19 | T021 | In Work | 9 |  | ED3002
2021-07-20 | T021 | In Work | 9 |  | ED3002
2021-07-21 | T021 | In Work | 9 |  | ED3002
2021-07-22 | T021 | In Work | 9 |  | ED3002
2021-07-23 | T021 | In Work | 9 |  | ED3002
2021-07-24 | T021 | In Work | 9 |  | ED3002
2021-07-25 | T021 | In Work | 9 |  | ED3002
2021-07-26 | T021 | In Work | 9 |  | ED3002
2021-07-27 | T021 | In Work | 9 |  | ED3002
2021-07-28 | T021 | In Work | 9 |  | ED3002
2021-07-29 | T021 | In Work | 9 |  | ED3002
2021-07-30 | T021 | In Work | 9 |  | ED3002
2021-07-31 | T021 | Delivered | 9 |  | ED3002
2021-08-01 | T018 | Rework | 9 |  | ED3002
2021-08-02 | T022 | In Work | 9 |  | ED3002
2021-08-03 | T022 | In Work | 9 |  | ED3002
2021-08-04 | T022 | In Work | 9 |  | ED3002
2021-08-05 | T022 | In Work | 9 |  | ED3002
2021-08-06 | T022 | In Work | 9 |  | ED3002
2021-08-07 | T022 | In Work | 9 |  | ED3002
2021-08-08 | T022 | In Work | 9 |  | ED3002
2021-08-09 | T022 | In Work | 9 |  | ED3002
2021-08-10 | T022 | Delivered | 9 |  | ED3002
2021-08-11 | T023 | In Work | 9 |  | ED3002
2021-08-12 | T023 | Delivered | 9 |  | ED3002
2021-08-13 | T024 | Delivered | 9 |  | ED3002
2021-08-14 | T025 | In Work | 9 |  | ED3002
2021-08-15 | T025 | In Work | 9 |  | ED3002
2021-08-16 | T025 | In Work | 9 |  | ED3002
2021-08-17 | T025 | In Work | 9 |  | ED3002
2021-08-18 | T025 | In Work | 9 |  | ED3002
2021-08-19 | T025 | In Work | 9 |  | ED3002
2021-08-20 | T025 | Delivered | 9 |  | ED3002
2021-08-21 | T020 | Rework | 9 |  | ED3002
2021-08-22 | T026 | Delivered | 9 |  | ED3002
2021-08-23 | T027 | In Work | 9 |  | ED3002
2021-08-24 | T027 | In Work | 9 |  | ED3002
2021-08-25 | T027 | In Work | 9 |  | ED3002
2021-08-26 | T027 | In Work | 9 |  | ED3002
2021-08-27 | T027 | In Work | 9 |  | ED3002
2021-08-28 | T027 | In Work | 9 |  | ED3002
2021-08-29 | T027 | Delivered | 9 |  | ED3002
2021-08-30 | T028 | In Work | 9 |  | ED3002
2021-08-31 | T028 | In Work | 9 |  | ED3002
2021-09-01 | T028 | In Work | 9 |  | ED3002
2021-09-02 | T028 | In Work | 9 |  | ED3002
2021-09-03 | T028 | In Work | 9 |  | ED3002
2021-09-04 | T028 | Delivered | 9 |  | ED3002
2021-09-05 | T029 | In Work | 9 |  | ED3002
2021-09-06 | T029 | Delivered | 9 |  | ED3002
2021-09-07 | T030 | In Work | 9 |  | ED3002
2021-09-08 | T030 | In Work | 9 |  | ED3002
2021-09-09 | T030 | In Work | 9 |  | ED3002
2021-09-10 | T030 | Delivered | 9 |  | ED3002

## Data
Status | EMPID
In Work | ED3002
On Hold
Delivered
Rejected
Rework