## Project Page
Task ID | Description | Planned Hours | Actual Hours | Planned Delivery Date | Actual Delivery Date | Task Status | OTD | FTR | Effort Variance | Remarks | EMPID
T031 |  | 72 | 72 | 2021-06-05 |  | Rework |  |  | 0% |  | ED3003
T032 |  | 117 | 117 | 2021-06-08 | 2021-06-08 | Delivered | OTD | YES | 0% |  | ED3003
T033 |  | 126 | 126 | 2021-09-13 |  | Rework |  |  | 0% |  | ED3003
T034 |  | 126 | 135 | 2021-07-04 | 2021-07-04 | Delivered | OTD | YES | 7.143% |  | ED3003
T035 |  | 81 | 81 | 2021-07-20 | 2021-07-19 | Delivered | OTD | YES | 0% |  | ED3003
T036 |  | 9 | 9 | 2021-07-20 | 2021-07-29 | Delivered | Non OTD | YES | 0% |  | ED3003
T037 |  | 45 | 45 | 2021-07-30 | 2021-07-30 | Delivered | OTD | YES | 0% |  | ED3003
T038 |  | 18 | 18 | 2021-08-09 | 2021-08-04 | Delivered | OTD | YES | 0% |  | ED3003
T039 |  | 126 | 126 | 2021-08-07 | 2021-08-07 | Delivered | OTD | YES | 0% |  | ED3003
T040 |  | 54 | 54 | 2021-08-21 | 2021-08-21 | Delivered | OTD | YES | 0% |  | ED3003
T041 |  | 9 | 9 | 2021-08-27 | 2021-08-27 | Delivered | OTD | YES | 0% |  | ED3003
T042 |  | 27 | 54 | 2021-08-30 | 2021-08-28 | Delivered | OTD | YES | 100% |  | ED3003
T043 |  | 36 | 45 | 2021-09-03 | 2021-09-03 | Delivered | OTD | YES | 25% |  | ED3003
T044 |  | 45 | 45 | 2021-09-08 | 2021-09-08 | Delivered | OTD | YES | 0% |  | ED3003
ED3003
Formulas:
Actual Delivery Date = IF(AND(Project_Tracker[[#This Row],[Task Status]]="Delivered", ISBLANK(Project_Tracker[[#This Row],[Planned Delivery Date]]) = FALSE), XLOOKUP(Project_Tracker[[#This Row],[Task ID]],Daily_Tracker[Task ID],Daily_Tracker[[Date ]], "",0,),"")

## Daily Tracker
Date | Task ID | Status | Hours | Remark | EMPID
2021-06-01 | T031 | In Work | 9 |  | ED3003
2021-06-02 | T031 | In Work | 9 |  | ED3003
2021-06-03 | T031 | In Work | 9 |  | ED3003
2021-06-04 | T031 | In Work | 9 |  | ED3003
2021-06-05 | T031 | In Work | 9 |  | ED3003
2021-06-06 | T031 | In Work | 9 |  | ED3003
2021-06-07 | T031 | Delivered | 9 |  | ED3003
2021-06-08 | T032 | In Work | 9 |  | ED3003
2021-06-09 | T032 | In Work | 9 |  | ED3003
2021-06-10 | T032 | In Work | 9 |  | ED3003
2021-06-11 | T032 | In Work | 9 |  | ED3003
2021-06-12 | T032 | In Work | 9 |  | ED3003
2021-06-13 | T032 | In Work | 9 |  | ED3003
2021-06-14 | T032 | In Work | 9 |  | ED3003
2021-06-15 | T032 | In Work | 9 |  | ED3003
2021-06-16 | T032 | In Work | 9 |  | ED3003
2021-06-17 | T032 | In Work | 9 |  | ED3003
2021-06-18 | T032 | In Work | 9 |  | ED3003
2021-06-19 | T032 | In Work | 9 |  | ED3003
2021-06-20 | T032 | Delivered | 9 |  | ED3003
2021-06-21 | T033 | In Work | 9 |  | ED3003
2021-06-22 | T033 | In Work | 9 |  | ED3003
2021-06-23 | T033 | In Work | 9 |  | ED3003
2021-06-24 | T033 | In Work | 9 |  | ED3003
2021-06-25 | T033 | In Work | 9 |  | ED3003
2021-06-26 | T033 | In Work | 9 |  | ED3003
2021-06-27 | T033 | In Work | 9 |  | ED3003
2021-06-28 | T033 | In Work | 9 |  | ED3003
2021-06-29 | T033 | In Work | 9 |  | ED3003
2021-06-30 | T033 | In Work | 9 |  | ED3003
2021-07-01 | T033 | In Work | 9 |  | ED3003
2021-07-02 | T033 | In Work | 9 |  | ED3003
2021-07-03 | T033 | Delivered | 9 |  | ED3003
2021-07-04 | T034 | In Work | 9 |  | ED3003
2021-07-05 | T034 | In Work | 9 |  | ED3003
2021-07-06 | T034 | In Work | 9 |  | ED3003
2021-07-07 | T034 | In Work | 9 |  | ED3003
2021-07-08 | T034 | In Work | 9 |  | ED3003
2021-07-09 | T034 | In Work | 9 |  | ED3003
2021-07-10 | T034 | In Work | 9 |  | ED3003
2021-07-11 | T034 | In Work | 9 |  | ED3003
2021-07-12 | T034 | In Work | 9 |  | ED3003
2021-07-13 | T034 | In Work | 9 |  | ED3003
2021-07-14 | T034 | In Work | 9 |  | ED3003
2021-07-15 | T034 | In Work | 9 |  | ED3003
2021-07-16 | T034 | In Work | 9 |  | ED3003
2021-07-17 | T034 | In Work | 9 |  | ED3003
2021-07-18 | T034 | Delivered | 9 |  | ED3003
2021-07-19 | T035 | In Work | 9 |  | ED3003
2021-07-20 | T035 | In Work | 9 |  | ED3003
2021-07-21 | T035 | In Work | 9 |  | ED3003
2021-07-22 | T035 | In Work | 9 |  | ED3003
2021-07-23 | T035 | In Work | 9 |  | ED3003
2021-07-24 | T035 | In Work | 9 |  | ED3003
2021-07-25 | T035 | In Work | 9 |  | ED3003
2021-07-26 | T035 | In Work | 9 |  | ED3003
2021-07-27 | T035 | Delivered | 9 |  | ED3003
2021-07-28 | T031 | Rework | 9 |  | ED3003
2021-07-29 | T036 | Delivered | 9 |  | ED3003
2021-07-30 | T037 | In Work | 9 |  | ED3003
2021-07-31 | T037 | In Work | 9 |  | ED3003
2021-08-01 | T037 | In Work | 9 |  | ED3003
2021-08-02 | T037 | In Work | 9 |  | ED3003
2021-08-03 | T037 | Delivered | 9 |  | ED3003
2021-08-04 | T038 | In Work | 9 |  | ED3003
2021-08-05 | T038 | Delivered | 9 |  | ED3003
2021-08-06 | T033 | Rework | 9 |  | ED3003
2021-08-07 | T039 | In Work | 9 |  | ED3003
2021-08-08 | T039 | In Work | 9 |  | ED3003
2021-08-09 | T039 | In Work | 9 |  | ED3003
2021-08-10 | T039 | In Work | 9 |  | ED3003
2021-08-11 | T039 | In Work | 9 |  | ED3003
2021-08-12 | T039 | In Work | 9 |  | ED3003
2021-08-13 | T039 | In Work | 9 |  | ED3003
2021-08-14 | T039 | In Work | 9 |  | ED3003
2021-08-15 | T039 | In Work | 9 |  | ED3003
2021-08-16 | T039 | In Work | 9 |  | ED3003
2021-08-17 | T039 | In Work | 9 |  | ED3003
2021-08-18 | T039 | In Work | 9 |  | ED3003
2021-08-19 | T039 | In Work | 9 |  | ED3003
2021-08-20 | T039 | Delivered | 9 |  | ED3003
2021-08-21 | T040 | In Work | 9 |  | ED3003
2021-08-22 | T040 | In Work | 9 |  | ED3003
2021-08-23 | T040 | In Work | 9 |  | ED3003
2021-08-24 | T040 | In Work | 9 |  | ED3003
2021-08-25 | T040 | In Work | 9 |  | ED3003
2021-08-26 | T040 | Delivered | 9 |  | ED3003
2021-08-27 | T041 | Delivered | 9 |  | ED3003
2021-08-28 | T042 | In Work | 9 |  | ED3003
2021-08-29 | T042 | In Work | 9 |  | ED3003
2021-08-30 | T042 | In Work | 9 |  | ED3003
2021-08-31 | T042 | In Work | 9 |  | ED3003
2021-09-01 | T042 | In Work | 9 |  | ED3003
2021-09-02 | T042 | Delivered | 9 |  | ED3003
2021-09-03 | T043 | In Work | 9 |  | ED3003
2021-09-04 | T043 | In Work | 9 |  | ED3003
2021-09-05 | T043 | In Work | 9 |  | ED3003
2021-09-06 | T043 | In Work | 9 |  | ED3003
2021-09-07 | T043 | Delivered | 9 |  | ED3003
2021-09-08 | T044 | In Work | 9 |  | ED3003
2021-09-09 | T044 | In Work | 9 |  | ED3003
2021-09-10 | T044 | In Work | 9 |  | ED3003
2021-09-11 | T044 | In Work | 9 |  | ED3003
2021-09-12 | T044 | Delivered | 9 |  | ED3003
2021-09-13 | T045 | In Work | 9 |  | ED3003
2021-09-14 | T045 | In Work | 9 |  | ED3003
2021-09-15 | T045 | In Work | 9 |  | ED3003

## Data
Requester | Project ID | Status | EMPID
Aditi Musunur | PD201 | In Work | ED3003
Advitiya Sujeet | PD202 | On Hold
Alagesan Poduri | PD203 | Delivered
Amrish Ilyas | PD204 | Rejected
Aprativirya Seshan | PD205 | Rework
Asvathama Ponnada | PD206
Avantas Ghosal | PD207
Avidosa Vaisakhi | PD208
Barsati Sandipa | PD119
Debasis Sundhararajan | PD120
Devasru Subramanyan | PD121
Dharmadhrt Ramila | PD122
Dhritiman Salim | PD123
Gopa Trilochana | PD124
Hardeep Suksma | PD125
Jayadev Mitali | PD126
Jitendra Choudhary | PD127
Kalyanavata Veerender | PD128
Naveen Tikaram | PD779
Vijai Sritharan | PD780
PD781
PD782
PD783
PD784
PD785
PD786
PD787
PD344
PD345
PD346
PD347
PD348
PD349
PD350
PD351
PD352
PD353