## Project Page
Task ID | Description | Planned Hours | Actual Hours | Planned Delivery Date | Actual Delivery Date | Task Status | OTD | FTR | Effort Variance | Remarks | EMPID
T045 |  | 27 | 27 | 2021-07-01 |  | Rework |  |  | 0% |  | ED3004
T046 |  | 81 | 81 | 2021-07-02 |  | Rework |  |  | 0% |  | ED3004
T047 |  | 108 | 117 | 2021-07-03 |  | Rework |  |  | 8.333% |  | ED3004
T048 |  | 99 | 90 | 2021-07-04 | 2021-06-24 | Delivered | OTD | YES | -9.091% |  | ED3004
T049 |  | 81 | 90 | 2021-07-05 | 2021-07-05 | Delivered | OTD | YES | 11.11% |  | ED3004
T050 |  | 108 | 108 | 2021-07-15 | 2021-07-15 | Delivered | OTD | YES | 0% |  | ED3004
T051 |  | 63 | 63 | 2021-07-07 |  | Rework |  |  | 0% |  | ED3004
T052 |  | 72 | 72 | 2021-08-03 | 2021-08-03 | Delivered | OTD | YES | 0% |  | ED3004
T053 |  | 9 | 9 | 2021-07-09 | 2021-08-11 | Delivered | Non OTD | YES | 0% |  | ED3004
T054 |  | 18 | 27 | 2021-08-12 | 2021-08-12 | Delivered | OTD | YES | 50% |  | ED3004
T055 |  | 117 | 117 | 2021-08-17 | 2021-08-15 | Delivered | OTD | YES | 0% |  | ED3004
T056 |  | 18 | 18 | 2021-08-30 | 2021-08-28 | Delivered | OTD | YES | 0% |  | ED3004
T057 |  | 63 | 63 | 2021-08-31 | 2021-08-31 | Delivered | OTD | NO | 0% |  | ED3004
T058 |  | 54 | 54 | 2021-09-07 | 2021-09-07 | Delivered | OTD | YES | 0% |  | ED3004
T059 |  | 36 | 27 | 2021-07-15 |  | In Work |  |  | -25% |  | ED3004
Formulas:
Actual Delivery Date = IF(AND(Project_Tracker[[#This Row],[Task Status]]="Delivered", ISBLANK(Project_Tracker[[#This Row],[Planned Delivery Date]]) = FALSE), XLOOKUP(Project_Tracker[[#This Row],[Task ID]],Daily_Tracker[Task ID],Daily_Tracker[[Date ]], "",0,),"")

## Daily Tracker
Date | Task ID | Status | Hours | Remark | EMPID
2021-06-01 | T045 | In Work | 9 |  | ED3004
2021-06-02 | T045 | Delivered | 9 |  | ED3004
2021-06-03 | T046 | In Work | 9 |  | ED3004
2021-06-04 | T046 | In Work | 9 |  | ED3004
2021-06-05 | T046 | In Work | 9 |  | ED3004
2021-06-06 | T046 | In Work | 9 |  | ED3004
2021-06-07 | T046 | In Work | 9 |  | ED3004
2021-06-08 | T046 | In Work | 9 |  | ED3004
2021-06-09 | T046 | In Work | 9 |  | ED3004
2021-06-10 | T046 | Delivered | 9 |  | ED3004
2021-06-11 | T045 | Rework | 9 |  | ED3004
2021-06-12 | T047 | In Work | 9 |  | ED3004
2021-06-13 | T047 | In Work | 9 |  | ED3004
2021-06-14 | T047 | In Work | 9 |  | ED3004
2021-06-15 | T047 | In Work | 9 |  | ED3004
2021-06-16 | T047 | In Work | 9 |  | ED3004
2021-06-17 | T047 | In Work | 9 |  | ED3004
2021-06-18 | T047 | In Work | 9 |  | ED3004
2021-06-19 | T047 | In Work | 9 |  | ED3004
2021-06-20 | T047 | In Work | 9 |  | ED3004
2021-06-21 | T047 | In Work | 9 |  | ED3004
2021-06-22 | T047 | In Work | 9 |  | ED3004
2021-06-23 | T047 | Delivered | 9 |  | ED3004
2021-06-24 | T048 | In Work | 9 |  | ED3004
2021-06-25 | T048 | In Work | 9 |  | ED3004
2021-06-26 | T048 | In Work | 9 |  | ED3004
2021-06-27 | T048 | In Work | 9 |  | ED3004
2021-06-28 | T048 | In Work | 9 |  | ED3004
2021-06-29 | T048 | In Work | 9 |  | ED3004
2021-06-30 | T048 | In Work | 9 |  | ED3004
2021-07-01 | T048 | In Work | 9 |  | ED3004
2021-07-02 | T048 | In Work | 9 |  | ED3004
2021-07-03 | T048 | Delivered | 9 |  | ED3004
2021-07-04 | T046 | Rework | 9 |  | ED3004
2021-07-05 | T049 | In Work | 9 |  | ED3004
2021-07-06 | T049 | In Work | 9 |  | ED3004
2021-07-07 | T049 | In Work | 9 |  | ED3004
2021-07-08 | T049 | In Work | 9 |  | ED3004
2021-07-09 | T049 | In Work | 9 |  | ED3004
2021-07-10 | T049 | In Work | 9 |  | ED3004
2021-07-11 | T049 | In Work | 9 |  | ED3004
2021-07-12 | T049 | In Work | 9 |  | ED3004
2021-07-13 | T049 | In Work | 9 |  | ED3004
2021-07-14 | T049 | Delivered | 9 |  | ED3004
2021-07-15 | T050 | In Work | 9 |  | ED3004
2021-07-16 | T050 | In Work | 9 |  | ED3004
2021-07-17 | T050 | In Work | 9 |  | ED3004
2021-07-18 | T050 | In Work | 9 |  | ED3004
2021-07-19 | T050 | In Work | 9 |  | ED3004
2021-07-20 | T050 | In Work | 9 |  | ED3004
2021-07-21 | T050 | In Work | 9 |  | ED3004
2021-07-22 | T050 | In Work | 9 |  | ED3004
2021-07-23 | T050 | In Work | 9 |  | ED3004
2021-07-24 | T050 | In Work | 9 |  | ED3004
2021-07-25 | T050 | In Work | 9 |  | ED3004
2021-07-26 | T050 | Delivered | 9 |  | ED3004
2021-07-27 | T047 | Rework | 9 |  | ED3004
2021-07-28 | T051 | In Work | 9 |  | ED3004
2021-07-29 | T051 | In Work | 9 |  | ED3004
2021-07-30 | T051 | In Work | 9 |  | ED3004
2021-07-31 | T051 | In Work | 9 |  | ED3004
2021-08-01 | T051 | In Work | 9 |  | ED3004
2021-08-02 | T051 | Delivered | 9 |  | ED3004
2021-08-03 | T052 | In Work | 9 |  | ED3004
2021-08-04 | T052 | In Work | 9 |  | ED3004
2021-08-05 | T052 | In Work | 9 |  | ED3004
2021-08-06 | T052 | In Work | 9 |  | ED3004
2021-08-07 | T052 | In Work | 9 |  | ED3004
2021-08-08 | T052 | In Work | 9 |  | ED3004
2021-08-09 | T052 | In Work | 9 |  | ED3004
2021-08-10 | T052 | Delivered | 9 |  | ED3004
2021-08-11 | T053 | Delivered | 9 |  | ED3004
2021-08-12 | T054 | In Work | 9 |  | ED3004
2021-08-13 | T054 | In Work | 9 |  | ED3004
2021-08-14 | T054 | Delivered | 9 |  | ED3004
2021-08-15 | T055 | In Work | 9 |  | ED3004
2021-08-16 | T055 | In Work | 9 |  | ED3004
2021-08-17 | T055 | In Work | 9 |  | ED3004
2021-08-18 | T055 | In Work | 9 |  | ED3004
2021-08-19 | T055 | In Work | 9 |  | ED3004
2021-08-20 | T055 | In Work | 9 |  | ED3004
2021-08-21 | T055 | In Work | 9 |  | ED3004
2021-08-22 | T055 | In Work | 9 |  | ED3004
2021-08-23 | T055 | In Work | 9 |  | ED3004
2021-08-24 | T055 | In Work | 9 |  | ED3004
2021-08-25 | T055 | In Work | 9 |  | ED3004
2021-08-26 | T055 | In Work | 9 |  | ED3004
2021-08-27 | T055 | Delivered | 9 |  | ED3004
2021-08-28 | T056 | In Work | 9 |  | ED3004
2021-08-29 | T056 | Delivered | 9 |  | ED3004
2021-08-30 | T051 | Rework | 9 |  | ED3004
2021-08-31 | T057 | In Work | 9 |  | ED3004
2021-09-01 | T057 | In Work | 9 |  | ED3004
2021-09-02 | T057 | In Work | 9 |  | ED3004
2021-09-03 | T057 | In Work | 9 |  | ED3004
2021-09-04 | T057 | In Work | 9 |  | ED3004
2021-09-05 | T057 | In Work | 9 |  | ED3004
2021-09-06 | T057 | Delivered | 9 |  | ED3004
2021-09-07 | T058 | In Work | 9 |  | ED3004
2021-09-08 | T058 | In Work | 9 |  | ED3004
2021-09-09 | T058 | In Work | 9 |  | ED3004
2021-09-10 | T058 | In Work | 9 |  | ED3004
2021-09-11 | T058 | In Work | 9 |  | ED3004
2021-09-12 | T058 | Delivered | 9 |  | ED3004
2021-09-13 | T059 | In Work | 9 |  | ED3004
2021-09-14 | T059 | In Work | 9 |  | ED3004
2021-09-15 | T059 | In Work | 9 |  | ED3004

## Data
Requester | Project ID | Status | EMPID
Aditi Musunur | PD201 | In Work | ED3004
Advitiya Sujeet | PD202 | On Hold
Alagesan Poduri | PD203 | Delivered
Amrish Ilyas | PD204 | Rejected
Aprativirya Seshan | PD205 | Rework
Asvathama Ponnada | PD206
Avantas Ghosal | PD207
Avidosa Vaisakhi | PD208
Barsati Sandipa | PD119
Debasis Sundhararajan | PD120
Devasru Subramanyan | PD121
Dharmadhrt Ramila | PD122
Dhritiman Salim | PD123
Gopa Trilochana | PD124
Hardeep Suksma | PD125
Jayadev Mitali | PD126
Jitendra Choudhary | PD127
Kalyanavata Veerender | PD128
Naveen Tikaram | PD779
Vijai Sritharan | PD780
PD781
PD782
PD783
PD784
PD785
PD786
PD787
PD344
PD345
PD346
PD347
PD348
PD349
PD350
PD351
PD352
PD353