## Project Page
Task ID | Description | Planned Hours | Actual Hours | Planned Delivery Date | Actual Delivery Date | Task Status | OTD | FTR | Effort Variance | Remarks | EMPID
T060 |  | 27 | 27 | 2021-06-11 |  | Rework |  | NO | 0% |  | ED3005
T061 |  | 63 | 72 | 2021-06-03 | 2021-06-03 | Delivered | OTD | YES | 14.29% |  | ED3005
T062 |  | 63 | 63 | 2021-06-20 | 2021-06-11 | Delivered | OTD | YES | 0% |  | ED3005
T063 |  | 72 | 72 | 2021-06-19 | 2021-06-18 | Delivered | OTD | YES | 0% |  | ED3005
T064 |  | 45 | 45 | 2021-06-27 | 2021-06-26 | Delivered | OTD | YES | 0% |  | ED3005
T065 |  | 36 | 36 | 2021-07-10 | 2021-07-01 | Delivered | OTD | YES | 0% |  | ED3005
T066 |  | 81 | 90 | 2021-07-05 | 2021-07-05 | Delivered | OTD | YES | 11.11% |  | ED3005
T067 |  | 81 | 81 | 2021-07-15 | 2021-07-15 | Delivered | OTD | YES | 0% |  | ED3005
T068 |  | 135 | 108 | 2021-07-26 | 2021-07-24 | Delivered | OTD | NO | -20% |  | ED3005
T069 |  | 9 | 9 | 2021-08-06 | 2021-08-05 | Delivered | OTD | NO | 0% |  | ED3005
T070 |  | 54 | 54 | 2021-08-06 | 2021-08-06 | Delivered | OTD | YES | 0% |  | ED3005
T071 |  | 126 | 117 | 2021-08-11 | 2021-08-12 | Delivered | Non OTD | YES | -7.143% |  | ED3005
T072 |  | 90 | 90 | 2021-08-26 | 2021-08-25 | Delivered | OTD | YES | 0% |  | ED3005
T073 |  | 9 | 9 | 2021-09-04 | 2021-09-04 | Delivered | OTD | YES | 0% |  | ED3005
T074 |  | 81 | 90 | 2021-09-07 | 2021-09-05 | Delivered | OTD | YES | 11.11% |  | ED3005
Formulas:
Actual Delivery Date = IF(AND(Project_Tracker[[#This Row],[Task Status]]="Delivered", ISBLANK(Project_Tracker[[#This Row],[Planned Delivery Date]]) = FALSE), XLOOKUP(Project_Tracker[[#This Row],[Task ID]],Daily_Tracker[Task ID],Daily_Tracker[[Date ]], "",0,),"")

## Daily Tracker
Date | Task ID | Status | Hours | Remark | EMPID
2021-06-01 | T060 | In Work | 9 |  | ED3005
2021-06-02 | T060 | Delivered | 9 |  | ED3005
2021-06-03 | T061 | In Work | 9 |  | ED3005
2021-06-04 | T061 | In Work | 9 |  | ED3005
2021-06-05 | T061 | In Work | 9 |  | ED3005
2021-06-06 | T061 | In Work | 9 |  | ED3005
2021-06-07 | T061 | In Work | 9 |  | ED3005
2021-06-08 | T061 | In Work | 9 |  | ED3005
2021-06-09 | T061 | In Work | 9 |  | ED3005
2021-06-10 | T061 | Delivered | 9 |  | ED3005
2021-06-11 | T062 | In Work | 9 |  | ED3005
2021-06-12 | T062 | In Work | 9 |  | ED3005
2021-06-13 | T062 | In Work | 9 |  | ED3005
2021-06-14 | T062 | In Work | 9 |  | ED3005
2021-06-15 | T062 | In Work | 9 |  | ED3005
2021-06-16 | T062 | In Work | 9 |  | ED3005
2021-06-17 | T062 | Delivered | 9 |  | ED3005
2021-06-18 | T063 | In Work | 9 |  | ED3005
2021-06-19 | T063 | In Work | 9 |  | ED3005
2021-06-20 | T063 | In Work | 9 |  | ED3005
2021-06-21 | T063 | In Work | 9 |  | ED3005
2021-06-22 | T063 | In Work | 9 |  | ED3005
2021-06-23 | T063 | In Work | 9 |  | ED3005
2021-06-24 | T063 | In Work | 9 |  | ED3005
2021-06-25 | T063 | Delivered | 9 |  | ED3005
2021-06-26 | T064 | In Work | 9 |  | ED3005
2021-06-27 | T064 | In Work | 9 |  | ED3005
2021-06-28 | T064 | In Work | 9 |  | ED3005
2021-06-29 | T064 | In Work | 9 |  | ED3005
2021-06-30 | T064 | Delivered | 9 |  | ED3005
2021-07-01 | T065 | In Work | 9 |  | ED3005
2021-07-02 | T065 | In Work | 9 |  | ED3005
2021-07-03 | T065 | In Work | 9 |  | ED3005
2021-07-04 | T065 | Delivered | 9 |  | ED3005
2021-07-05 | T066 | In Work | 9 |  | ED3005
2021-07-06 | T066 | In Work | 9 |  | ED3005
2021-07-07 | T066 | In Work | 9 |  | ED3005
2021-07-08 | T066 | In Work | 9 |  | ED3005
2021-07-09 | T066 | In Work | 9 |  | ED3005
2021-07-10 | T066 | In Work | 9 |  | ED3005
2021-07-11 | T066 | In Work | 9 |  | ED3005
2021-07-12 | T066 | In Work | 9 |  | ED3005
2021-07-13 | T066 | In Work | 9 |  | ED3005
2021-07-14 | T066 | Delivered | 9 |  | ED3005
2021-07-15 | T067 | In Work | 9 |  | ED3005
2021-07-16 | T067 | In Work | 9 |  | ED3005
2021-07-17 | T067 | In Work | 9 |  | ED3005
2021-07-18 | T067 | In Work | 9 |  | ED3005
2021-07-19 | T067 | In Work | 9 |  | ED3005
2021-07-20 | T067 | In Work | 9 |  | ED3005
2021-07-21 | T067 | In Work | 9 |  | ED3005
2021-07-22 | T067 | In Work | 9 |  | ED3005
2021-07-23 | T067 | Delivered | 9 |  | ED3005
2021-07-24 | T068 | In Work | 9 |  | ED3005
2021-07-25 | T068 | In Work | 9 |  | ED3005
2021-07-26 | T068 | In Work | 9 |  | ED3005
2021-07-27 | T068 | In Work | 9 |  | ED3005
2021-07-28 | T068 | In Work | 9 |  | ED3005
2021-07-29 | T068 | In Work | 9 |  | ED3005
2021-07-30 | T068 | In Work | 9 |  | ED3005
2021-07-31 | T068 | In Work | 9 |  | ED3005
2021-08-01 | T068 | In Work | 9 |  | ED3005
2021-08-02 | T068 | In Work | 9 |  | ED3005
2021-08-03 | T068 | Delivered | 9 |  | ED3005
2021-08-04 | T068 | Delivered | 9 |  | ED3005
2021-08-05 | T069 | Delivered | 9 |  | ED3005
2021-08-06 | T070 | In Work | 9 |  | ED3005
2021-08-07 | T070 | In Work | 9 |  | ED3005
2021-08-08 | T070 | In Work | 9 |  | ED3005
2021-08-09 | T070 | In Work | 9 |  | ED3005
2021-08-10 | T070 | In Work | 9 |  | ED3005
2021-08-11 | T070 | Delivered | 9 |  | ED3005
2021-08-12 | T071 | In Work | 9 |  | ED3005
2021-08-13 | T071 | In Work | 9 |  | ED3005
2021-08-14 | T071 | In Work | 9 |  | ED3005
2021-08-15 | T071 | In Work | 9 |  | ED3005
2021-08-16 | T071 | In Work | 9 |  | ED3005
2021-08-17 | T071 | In Work | 9 |  | ED3005
2021-08-18 | T071 | In Work | 9 |  | ED3005
2021-08-19 | T071 | In Work | 9 |  | ED3005
2021-08-20 | T071 | In Work | 9 |  | ED3005
2021-08-21 | T071 | In Work | 9 |  | ED3005
2021-08-22 | T071 | In Work | 9 |  | ED3005
2021-08-23 | T071 | In Work | 9 |  | ED3005
2021-08-24 | T071 | Delivered | 9 |  | ED3005
2021-08-25 | T072 | In Work | 9 |  | ED3005
2021-08-26 | T072 | In Work | 9 |  | ED3005
2021-08-27 | T072 | In Work | 9 |  | ED3005
2021-08-28 | T072 | In Work | 9 |  | ED3005
2021-08-29 | T072 | In Work | 9 |  | ED3005
2021-08-30 | T072 | In Work | 9 |  | ED3005
2021-08-31 | T072 | In Work | 9 |  | ED3005
2021-09-01 | T072 | In Work | 9 |  | ED3005
2021-09-02 | T072 | In Work | 9 |  | ED3005
2021-09-03 | T072 | Delivered | 9 |  | ED3005
2021-09-04 | T073 | Delivered | 9 |  | ED3005
2021-09-05 | T074 | In Work | 9 |  | ED3005
2021-09-06 | T074 | In Work | 9 |  | ED3005
2021-09-07 | T074 | In Work | 9 |  | ED3005
2021-09-08 | T074 | In Work | 9 |  | ED3005
2021-09-09 | T074 | In Work | 9 |  | ED3005
2021-09-10 | T074 | In Work | 9 |  | ED3005
2021-09-11 | T074 | In Work | 9 |  | ED3005
2021-09-12 | T074 | In Work | 9 |  | ED3005
2021-09-13 | T074 | In Work | 9 |  | ED3005
2021-09-14 | T074 | Delivered | 9 |  | ED3005
2021-09-15 | T060 | Rework | 9 |  | ED3005

## Data
Requester | Project ID | Status | EMPID
Aditi Musunur | PD201 | In Work | ED3005
Advitiya Sujeet | PD202 | On Hold
Alagesan Poduri | PD203 | Delivered
Amrish Ilyas | PD204 | Rejected
Aprativirya Seshan | PD205 | Rework
Asvathama Ponnada | PD206
Avantas Ghosal | PD207
Avidosa Vaisakhi | PD208
Barsati Sandipa | PD119
Debasis Sundhararajan | PD120
Devasru Subramanyan | PD121
Dharmadhrt Ramila | PD122
Dhritiman Salim | PD123
Gopa Trilochana | PD124
Hardeep Suksma | PD125
Jayadev Mitali | PD126
Jitendra Choudhary | PD127
Kalyanavata Veerender | PD128
Naveen Tikaram | PD779
Vijai Sritharan | PD780
PD781
PD782
PD783
PD784
PD785
PD786
PD787
PD344
PD345
PD346
PD347
PD348
PD349
PD350
PD351
PD352
PD353